# Real-Time Email Security Detection System

## Implementation Phases & Development Plan

Version: 1.0
Date: January 2026
Classification: Project Management - Technical Roadmap

# Executive Summary

This document provides a detailed, step-by-step implementation plan for developing the Real-Time Email Security Detection System. The project is structured into five distinct phases over a 16-week development cycle, with clear deliverables, milestones, and success criteria for each phase.

The phased approach balances rapid prototyping with thorough validation, allowing for iterative refinement based on testing feedback. Each phase builds upon the previous one, gradually transforming research and design into a production-ready system.

Key Implementation Strategy:
• Agile methodology with 2-week sprints
• Continuous integration and testing throughout
• Incremental feature delivery with regular demos
• Risk mitigation through parallel workstreams
• Early user feedback integration (beta testing in Phase 5)

Total Timeline: 16 weeks from project initiation to production-ready system
Team Size: 2-3 developers working part-time (15-20 hours/week each)
Budget: $0-100 for cloud resources and API credits

# Development Methodology

## Agile Framework

We adopt an agile development approach with the following practices:

Sprint Structure:
• Sprint length: 2 weeks
• Sprint planning: Monday of week 1 (1 hour)
• Daily standups: 15 minutes (async via Slack acceptable)
• Sprint review/demo: Friday of week 2 (1 hour)
• Sprint retrospective: Friday of week 2 (30 minutes)

Work Prioritization:
• MoSCoW method: Must have, Should have, Could have, Won't have
• Story points for estimation (Fibonacci sequence)
• Velocity tracking to improve predictability

Tools and Infrastructure:
• Version Control: Git + GitHub
• Project Management: GitHub Projects or Jira
• Documentation: Confluence or Notion
• Communication: Slack or Discord
• CI/CD: GitHub Actions
• Code Review: Pull requests with 1+ approver required

Quality Standards:
• Code coverage target: >80%
• All features require tests before merge
• Linting and formatting enforced (Black, Flake8, ESLint)
• Security scanning on every PR
• Performance benchmarks for critical paths

# Phase 1: Research & Planning (Weeks 1-2)

## Overview

Foundation phase focused on understanding the problem space, evaluating existing solutions, collecting datasets, and finalizing technical decisions. This phase ensures the team has a shared understanding of project goals and a clear technical roadmap before writing production code.

## Key Objectives

Comprehensive literature review of email security threats and detection techniques

Dataset acquisition and preliminary quality assessment

Technology stack finalization with proof-of-concept validations

Detailed system architecture design with component specifications

Development environment setup and team onboarding

## Detailed Tasks

### Week 1: Research & Dataset Collection

#### Literature Review (8 hours)

Review academic papers on phishing detection (IEEE, ACM Digital Library)

Analyze existing solutions (Gmail, Outlook spam filters, commercial tools)

Study OWASP guidelines for email security

Document findings in shared knowledge base

#### Dataset Acquisition (6 hours)

Download PhishTank database (latest dump)

Acquire APWG eCrime Research dataset

Download SpamAssassin Public Corpus

Obtain Enron Email Dataset (for legitimate examples)

Document dataset statistics (size, date range, class distribution)

#### Preliminary Data Analysis (4 hours)

Inspect data formats and schemas

Check for duplicates and missing values

Analyze class imbalance ratios

Identify data quality issues requiring preprocessing

Create exploratory data analysis (EDA) notebook

### Week 2: Technical Design & Setup

#### Technology Stack Validation (6 hours)

Create proof-of-concept for IMAP connection with Gmail/Outlook

Test XGBoost and DistilBERT model loading and inference speed

Validate database schema design (PostgreSQL)

Test notification delivery via email and desktop

Document findings and confirm final technology selections

#### System Architecture Design (6 hours)

Create detailed architecture diagrams (use draw.io or Lucidchart)

Define API endpoints and data contracts

Design database schema with migrations

Specify service boundaries and interfaces

Document scalability and security considerations

#### Development Environment Setup (6 hours)

Set up Git repository with branch protection rules

Create Docker Compose configuration for local development

Configure PostgreSQL and Redis containers

Set up Python virtual environment and requirements.txt

Configure linting, formatting, and pre-commit hooks

Create GitHub Actions workflow for CI/CD

Set up monitoring (Prometheus + Grafana) in development

## Phase 1 Deliverables

Research findings report with references

Dataset collection (50k+ labeled emails ready for preprocessing)

Finalized technology stack document

System architecture diagrams and specifications

Development environment ready for all team members

Project charter with roles, responsibilities, and communication plan

## Success Criteria

All team members have working development environment

Datasets downloaded and quality-assessed

Technology choices validated through proof-of-concepts

Architecture document reviewed and approved by all stakeholders

Project board populated with Phase 2 tasks

# Phase 2: Foundation Development (Weeks 3-6)

## Overview

Core infrastructure development phase. Build the foundational components that all other features depend on: IMAP integration, database layer, feature extraction pipeline, and basic API framework. By end of Phase 2, the system can connect to email accounts, retrieve emails, extract features, and store data.

## Key Objectives

Implement robust IMAP client with error handling and reconnection logic

Design and implement database schema with proper indexing

Build comprehensive feature extraction pipeline

Process and clean training datasets

Create REST API foundation with authentication

## Detailed Tasks by Sprint

### Sprint 2 (Weeks 3-4): IMAP & Database

#### IMAP Integration Layer (16 hours)

Implement IMAPClient class with connection pooling

Support Gmail, Outlook, and generic IMAP servers

Implement OAuth2 authentication flow for Gmail/Outlook

Handle IDLE mode for real-time notifications

Add exponential backoff for rate limiting

Write unit tests for connection handling

Create mock IMAP server for testing

#### Database Design & Implementation (12 hours)

Design PostgreSQL schema (users, accounts, emails, features, alerts)

Implement SQLAlchemy models with relationships

Create Alembic migrations

Add indexes for frequently queried fields

Implement connection pooling (PgBouncer)

Write database access layer (repository pattern)

Create seed data for development/testing

#### Configuration Management (4 hours)

Implement config loading from environment variables

Create config validation schema

Set up secrets management (encrypted credentials)

Document configuration options

### Sprint 3 (Weeks 5-6): Feature Extraction & Data Processing

#### Feature Extraction Pipeline (18 hours)

Implement header feature extractors (SPF, DKIM, domain age, etc)

Implement content feature extractors (text stats, HTML parsing)

Implement URL feature extractors (domain reputation, shorteners)

Implement attachment feature extractors (file types, sizes)

Create feature aggregator and validator

Add caching layer for expensive operations (domain lookups)

Write comprehensive unit tests for each extractor

Create feature extraction performance benchmarks

#### Dataset Preprocessing (12 hours)

Clean PhishTank data (remove duplicates, invalid entries)

Process Enron dataset (filter PII, validate legitimacy)

Merge all datasets into unified format

Balance dataset or apply class weights

Split into train/validation/test (70/15/15)

Generate feature vectors for entire dataset

Store processed features in database

Document dataset statistics and preprocessing steps

#### API Framework (6 hours)

Set up FastAPI project structure

Implement JWT-based authentication

Create user registration and login endpoints

Add middleware (CORS, rate limiting, logging)

Generate OpenAPI/Swagger documentation

Write integration tests for auth flows

## Phase 2 Deliverables

IMAP service connecting to Gmail, Outlook, generic IMAP servers

PostgreSQL database with all tables and migrations

Feature extraction library with 50+ features implemented

Preprocessed training dataset (50k+ examples with features)

REST API with authentication and basic endpoints

Comprehensive test suite (unit + integration) with >70% coverage

Technical documentation for all components

## Success Criteria

IMAP connection successful to at least 3 different email providers

Feature extraction completes in <1 second per email

All 50+ features correctly extracted and validated

Training dataset processed and stored in database

API authentication working with JWT tokens

All tests passing in CI pipeline

# Phase 3: ML Model Development (Weeks 7-10)

## Overview

Machine learning core development. Train, evaluate, and optimize detection models. This phase transforms the feature-rich dataset into production-ready classifiers. Focus on achieving target metrics (95% precision, 92% recall) while maintaining inference speed requirements.

## Key Objectives

Train baseline models (Logistic Regression, Random Forest)

Optimize XGBoost with hyperparameter tuning

Fine-tune DistilBERT on email text

Build and optimize ensemble model

Achieve target performance metrics on test set

### Sprint 4 (Weeks 7-8): Baseline Models & XGBoost

#### Baseline Model Training (8 hours)

Implement training pipeline (data loading, preprocessing)

Train Logistic Regression with L2 regularization

Train Random Forest (300 trees, max_depth=20)

Evaluate on validation set

Generate classification reports and confusion matrices

Document baseline metrics (target F1: 85-90%)

Analyze feature importance from Random Forest

#### XGBoost Development (16 hours)

Implement XGBoost training pipeline

Grid search hyperparameters (depth, learning rate, trees)

Use 5-fold cross-validation for tuning

Implement early stopping on validation loss

Analyze feature importance with SHAP values

Perform feature selection (keep top 80% by importance)

Retrain with selected features

Achieve F1 ≥ 94% on validation set

Export model to ONNX format

Benchmark inference latency

#### Model Interpretability (4 hours)

Generate SHAP summary plots

Create feature importance visualizations

Implement explain_prediction() function

Document interpretation methodology

### Sprint 5 (Weeks 9-10): DistilBERT & Ensemble

#### DistilBERT Fine-Tuning (14 hours)

Prepare text dataset (subject + body, max 512 tokens)

Load pre-trained distilbert-base-uncased

Implement training loop with HuggingFace Transformers

Fine-tune for 3-5 epochs (learning rate 2e-5)

Use mixed precision training for speed (if GPU available)

Implement early stopping on validation loss

Evaluate on validation set (target F1: 92%)

Export to ONNX format

Benchmark inference latency

Visualize attention weights for sample emails

#### Ensemble Model (8 hours)

Generate predictions from XGBoost and DistilBERT on validation set

Grid search ensemble weights (0.5-0.8 for XGBoost)

Optimize for F1 with constraint: precision ≥ 95%

Implement EnsembleClassifier class

Evaluate ensemble on validation set (target F1: 96%)

Create combined explanation function (XGB features + BERT attention)

#### Model Evaluation & Testing (6 hours)

Evaluate ensemble on held-out test set

Generate comprehensive evaluation report

Perform error analysis (analyze false positives/negatives)

Test on adversarial examples (if available)

Benchmark end-to-end inference time

Document model performance and limitations

## Phase 3 Deliverables

Trained XGBoost model (ONNX format) achieving F1 ≥ 94%

Fine-tuned DistilBERT model (ONNX format) achieving F1 ≥ 92%

Ensemble classifier achieving F1 ≥ 96% on test set

Model evaluation report with metrics and error analysis

Model explanation functions for interpretability

Model artifacts registered in MLflow

Inference benchmarks showing <500ms latency

## Success Criteria

Test set precision ≥ 95%

Test set recall ≥ 92%

Test set F1 score ≥ 93%

P95 inference latency < 500ms

Models successfully exported to ONNX

Interpretable explanations generated for sample predictions

# Phase 4: Integration & Interface (Weeks 11-14)

## Overview

System integration phase. Connect all components into a cohesive application with user-facing interfaces. Implement alert management, build the web dashboard, complete API endpoints, and deploy models into the serving infrastructure. By end of Phase 4, the system is feature-complete and ready for testing.

## Key Objectives

Implement alert generation and notification delivery

Build React-based web dashboard

Complete all REST API endpoints

Deploy models with ONNX Runtime

Integrate all components into end-to-end pipeline

### Sprint 6 (Weeks 11-12): Alert System & Backend Completion

#### Alert Management System (14 hours)

Implement alert generation based on threat scores

Create notification templates (email, desktop, push)

Implement rate limiting (max 10 alerts/hour per user)

Add deduplication logic (group similar threats)

Implement alert delivery via multiple channels:

- Email notifications

- Desktop notifications (native OS)

- Mobile push (Firebase Cloud Messaging)

- Webhook integrations

Set up Celery workers for async delivery

Add retry logic with exponential backoff

Create alert history and status tracking

#### API Completion (10 hours)

Implement IMAP account management endpoints (CRUD)

Implement user preferences endpoints

Implement email review endpoints (flagged emails list)

Implement threat explanation endpoint

Implement whitelist/blacklist management

Implement analytics endpoints (stats, trends)

Add WebSocket endpoint for real-time updates

Write integration tests for all endpoints

Generate complete API documentation

#### Model Serving Infrastructure (8 hours)

Set up ONNX Runtime for model inference

Implement model loading and caching

Create prediction service with batching support

Add model versioning and rollback capability

Implement health check endpoint

Add performance monitoring (latency, throughput)

Write load tests for model serving

### Sprint 7 (Weeks 13-14): Dashboard Development

#### Dashboard Setup (4 hours)

Initialize React project with TypeScript

Set up routing (React Router)

Configure Redux Toolkit for state management

Set up Material-UI component library

Implement authentication flow (login, register)

Create protected route wrapper

#### Core Dashboard Views (18 hours)

Build main dashboard with threat statistics

Implement email review interface:

- Flagged email list with filters

- Email detail view with threat explanation

- Quick actions (whitelist, delete, report)

Build configuration panel:

- IMAP account management

- Notification preferences

- Threshold adjustments

Build analytics dashboard:

- Historical threat trends (Recharts)

- Detection performance metrics

- Account activity monitoring

Implement responsive design (mobile/tablet/desktop)

Add dark mode support

#### Real-time Features (4 hours)

Integrate Socket.IO client for WebSocket

Implement real-time alert notifications

Add live threat count updates

Implement toast notifications for user actions

#### Frontend Testing (4 hours)

Write unit tests for React components

Write integration tests for user flows

Perform accessibility audit (WCAG 2.1 AA)

Test on multiple browsers and devices

## Phase 4 Deliverables

Functional alert system with multi-channel delivery

Complete REST API with all endpoints documented

React dashboard with all core views implemented

Model serving infrastructure with ONNX Runtime

End-to-end system integration (IMAP → Detection → Alert → UI)

WebSocket real-time updates

Comprehensive test suite for frontend and backend

## Success Criteria

User can register, login, and configure IMAP accounts

System successfully detects and flags threats in real-time

Alerts delivered via at least 2 channels (email + desktop)

Dashboard displays flagged emails with explanations

All API endpoints functional and tested

End-to-end flow completed in <5 seconds (email arrival → alert)

UI responsive on mobile, tablet, and desktop

# Phase 5: Testing & Refinement (Weeks 15-16)

## Overview

Final phase focused on comprehensive testing, bug fixing, performance optimization, security hardening, and documentation completion. Includes beta testing with real users to gather feedback and validate usability. Prepare portfolio materials and deployment documentation.

## Key Objectives

Comprehensive testing (functional, performance, security)

Beta testing with 5-10 users

Bug fixing and performance optimization

Security audit and vulnerability remediation

Complete documentation and portfolio materials

### Sprint 8 (Week 15): Testing & Security

#### Comprehensive Testing (12 hours)

Run full test suite (unit + integration + e2e)

Perform manual testing of all user workflows

Load testing: simulate 100+ concurrent users

Stress testing: push system to failure points

Test with different email providers and configurations

Test error scenarios (network failures, invalid data)

Document all bugs in issue tracker

#### Security Audit (10 hours)

Run automated security scanners (Snyk, Bandit)

Review OWASP Top 10 compliance

Test SQL injection vulnerabilities

Test XSS vulnerabilities in dashboard

Review authentication and authorization logic

Audit credential storage and encryption

Test rate limiting and DoS protection

Review API endpoint security

Document findings and remediate critical/high issues

#### Performance Optimization (8 hours)

Profile API endpoints and identify bottlenecks

Optimize slow database queries

Add missing database indexes

Optimize feature extraction pipeline

Implement caching where beneficial

Reduce model inference latency

Document performance improvements

### Sprint 9 (Week 16): Beta Testing & Documentation

#### Beta Testing Program (12 hours)

Recruit 5-10 beta testers (friends, colleagues, online community)

Provide setup instructions and support

Collect feedback via surveys and interviews

Monitor system performance with real users

Track and prioritize feedback

Fix critical bugs discovered during beta

Iterate on UX based on feedback

#### Documentation Completion (10 hours)

Write comprehensive README with setup instructions

Create user manual with screenshots

Write developer guide for contributors

Document API with examples

Create architecture documentation

Write deployment guide (Docker, cloud platforms)

Document security and privacy policies

Create troubleshooting guide

#### Portfolio Materials (8 hours)

Write project overview and motivation

Document technical decisions and trade-offs

Create demo video (3-5 minutes) showcasing features

Take screenshots for portfolio

Write blog post about development experience

Prepare presentation slides for interviews

Update GitHub README with badges and visuals

## Phase 5 Deliverables

Comprehensive test results and coverage reports

Security audit report with all critical issues resolved

Beta testing feedback summary and improvements implemented

Complete user and developer documentation

Demo video showcasing system capabilities

Portfolio writeup with technical highlights

Production-ready deployment scripts

Final release (v1.0.0) tagged in Git

## Success Criteria

All critical and high-priority bugs fixed

Test coverage ≥ 80%

Security audit shows no critical vulnerabilities

Beta testers successfully set up and use system

System uptime ≥ 99% during beta testing period

Documentation complete and reviewed

Demo video completed and uploaded

Project ready for public release or portfolio showcase

# Risk Management & Contingency Plans

### Timeline Slippage (Severity: Medium)

Risk: Tasks take longer than estimated, delaying milestones.
Mitigation: Build 10% buffer into each phase. Track velocity and adjust scope if needed. Prioritize must-have features over nice-to-haves. Communicate early if delays anticipated.

### Technical Blockers (Severity: Medium)

Risk: Unexpected technical challenges (e.g., IMAP provider restrictions, model performance issues).
Mitigation: Allocate time for research and problem-solving. Maintain active communication with team. Have alternative approaches documented. Don't be afraid to pivot if necessary.

### Scope Creep (Severity: High)

Risk: Feature requests and new ideas expand project beyond original scope.
Mitigation: Maintain strict adherence to defined scope. Track all new ideas in backlog for v2.0. Review scope weekly. Get team alignment before adding features.

### Resource Constraints (Severity: Low)

Risk: Team members unavailable due to other commitments.
Mitigation: Part-time timeline accounts for limited availability. Cross-train team members. Document work thoroughly for knowledge sharing. Adjust timeline if extended absences occur.

### Data Quality Issues (Severity: Medium)

Risk: Training data insufficient or biased, leading to poor model performance.
Mitigation: Evaluate multiple datasets early. Implement data quality checks. Be prepared to augment with synthetic data or additional sources. Accept slightly lower initial metrics if data-limited.

### Performance Problems (Severity: Low)

Risk: System doesn't meet speed requirements (<500ms inference).
Mitigation: Early performance benchmarking. ONNX conversion for optimization. Caching strategies. Worst case: deploy smaller/faster model with slight accuracy trade-off.

# Timeline Summary & Milestones

| Phase | Duration | Key Milestone | Go/No-Go Decision |
| --- | --- | --- | --- |
| Phase 1: Research & Planning | Weeks 1-2 | Architecture design complete | Proceed if team aligned on tech stack |
| Phase 2: Foundation Development | Weeks 3-6 | IMAP + features working | Proceed if features extract in <1s |
| Phase 3: ML Model Development | Weeks 7-10 | Models hit target metrics | Proceed if F1 ≥ 93% |
| Phase 4: Integration & Interface | Weeks 11-14 | Full system operational | Proceed if e2e flow works |
| Phase 5: Testing & Refinement | Weeks 15-16 | Production ready | Launch if security audit passes |

# Final Notes on Implementation

This implementation plan provides a structured roadmap from concept to production-ready system. Key success factors:

Flexibility: While the plan is detailed, remain adaptable. If something isn't working, pivot quickly rather than forcing a solution.

Communication: Maintain open communication within the team and with stakeholders. Regular demos keep everyone aligned and motivated.

Incremental Value: Each phase delivers tangible value and can be demoed. This builds momentum and validates progress.

Technical Debt: Balance speed with quality. Some shortcuts are acceptable in early phases if documented and addressed before production.

User Focus: Keep end-users in mind throughout development. The best technical system is useless if users don't adopt it.

Portfolio Context: Remember this is also a portfolio project. Document decisions, challenges, and learnings. The journey is as valuable as the destination.

Post-v1.0 Roadmap:
Once v1.0 launches, consider these enhancements for future versions:
• Multi-language support
• Browser extension for webmail
• Mobile native apps
• Advanced threat intelligence integration
• Collaborative filtering between users
• Enterprise features (multi-tenant, admin console)

Timeline Contingency:
If the 16-week timeline proves too aggressive, the project can be compressed by:
• Reducing dashboard polish (focus on functionality over UI/UX)
• Using single model instead of ensemble (XGBoost only)
• Limiting to Gmail-only support initially
• Deferring analytics dashboard to v1.1

Conversely, if development goes faster than expected, use extra time for:
• Additional testing and quality assurance
• Performance optimizations
• Enhanced documentation
• Earlier beta testing with more users